## Excel Sprint Project Tracker
Sprint Project Tracker Web Accounting | [8 empty] | Task in Progress | [5 empty] | Task Completed
[8 empty] | 2021-03-12 |  |  |  |  | 2021-03-19 |  |  |  |  | 2021-03-26 |  |  |  |  | 2021-04-02 |  |  |  |  | 2021-04-09 |  |  |  |  | 2021-04-16 |  |  |  |  | 2021-04-23
PROJECT START DATE | 2021-03-11 |  | SCROLL TO WEEK # |  | 1
Sprint | Priority | Start | Finish | Duration | Status | % Complete |  | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-22 | 2021-03-23 | 2021-03-24 | 2021-03-25 | 2021-03-26 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23
[8 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Project Summary |  | 2021-03-11 | 2021-04-23 | 32 day(s) |  | 55.83%
#1 Penyiapan database |  | 2021-03-11 | 2021-03-15 | 3 day(s)
Analisis kebutuhan database | Medium | 2021-03-11 | 2021-03-12 | 2 day(s) | Yellow | 100%
Membuat rancangan database dan menentukan relasi antar tabel | Medium | 2021-03-12 | 2021-03-13 | 1 day(s) | Yellow | 100% | 0
Membuat model db dengan sequelize | Low | 2021-03-13 | 2021-03-15 | 1 day(s) | Green | 100%
#2 Pengerjaan Backend (Restful API) dengan Express Js |  | 2021-03-16 | 2021-03-22 | 5 day(s)
Mendefinisikan end point yang dibutuhkan frontend | Low | 2021-03-16 | 2021-03-17 | 2 day(s) | Green | 90%
Membuat fitur login, register, send email | High | 2021-03-17 | 2021-03-18 | 2 day(s) | Red | 90%
Membuat fitur CRUD, validasi data, dan conditonal rendering | Medium | 2021-03-18 | 2021-03-22 | 3 day(s) | Yellow | 100%
#3 Pengerjaan Frontend (membuat halaman dan mengintegrasikan dengan backend) |  | 2021-03-23 | 2021-04-06 | 11 day(s)
Membuat tampilan static website | Medium | 2021-03-23 | 2021-03-30 | 6 day(s) | Yellow | 90%
Mendefinisikan action dan reducer pada redux sebagai manajemen state. Mengintegrasikan register, login, dan reset password | Medium | 2021-03-31 | 2021-04-02 | 3 day(s) | Yellow | 0%
Memberi fungsi conditional rendering, Integrasi halaman web dengan end point | High | 2021-04-02 | 2021-04-06 | 3 day(s) | Red | 0%
#4 Deploy, UAT, Go Live Trail |  | 2021-04-07 | 2021-04-23 | 13 day(s)
Build, deploy, and testing | Medium | 2021-04-07 | 2021-04-12 | 4 day(s) | Yellow | 0%
UAT | Medium | 2021-04-13 | 2021-04-16 | 4 day(s) | Yellow | 0%
Go lIve Trial | Low | 2021-04-19 | 2021-04-23 | 5 day(s) | Green | 0%
Libur Hari Raya